## Implementation Plan
# | Task | Prerequisites | Expected Duration[Day/Week] | Owner | Status
PROJECT IMPLEMENTATION PLAN
Phase 1 – Planning & Requirements
1 | Conduct kickoff meeting with Najm | Stakeholders availability | 2 day | Project Manager / Najm Team
2 | Site Preparation | Prepare Server | 1 day | Project Manager / Najm Team
3 | Finalize functional requirements (Ticket Number passing, UCID mapping, DB schema, API details) | Kickoff completed | 2 days | Project Manager / Senior Developer / Najm IT
4 | Confirm integration points (CRM, One-X Agent, ACR) | Requirements workshop | 2 days | Senior Developer / Najm IT
5 | Define UAT test scenarios | Requirements document finalized | 1 day | QA / Najm Team / Senior Developer
Phase 2 – Design & Development
1 | Design DB | Requirements finalized | 3 days | Senior Developer
2 | Develop custom app (DB integration, ACR API integration) | DB schema ready | 15 days | Senior Developer
3 | Build API layer to connect with Najm CRM | CRM test environment available | 7 days | Senior Developer / Najm IT
Phase 3 – Integration & SIT
1 | Integrate app with One‑X Agent, ACR, and CRM | Development completed | 3 days | Senior Developer / Najm IT
2 | System Integration Testing (UCID↔Ticket mapping, DB checks, API validation) | Test environment ready | 3 days | QA / Najm Team
3 | Fix defects & refine application | SIT report | 2 day | Senior Developer
Phase 4 – User Acceptance Testing (UAT)
1 | Support Najm users during UAT | SIT completed | 2 days | QA / Najm Team
2 | Validate end‑to‑end workflows | Test data prepared | 2 days | QA / Najm Team
3 | Collect feedback and implement refinements | UAT execution | 2 days | Senior Developer
Phase 5 – Go‑Live
1 | Deploy application in production | UAT sign‑off | 5 days | Senior Developer / Najm IT
2 | Provide technical documentation and user guides | Documentation completed | 2 days | Senior Developer / Project Manager
Phase 6 – Post‑Go‑Live Support
1 | Technical support for issues & minor enhancements | Production Go‑Live | Ongoing | Support Team
2 | SLA‑driven response to support requests | Signed support agreement | Ongoing | Support Team